## Instructions
Instructions | Enter your team name as specified in the cell below. When doing cross-team and Freshman Seminar acceptance testing, enter the name for the testing group. Fill-in the Test Plan worksheet with all the remaining User Stories in your Product Backlog. As your user stories are refined, add the acceptance criteria for each user story. Use a separate worksheet to provide any specific test case data that the tester needs to use. As tests are performed in each sprint, indicate Pass/Fail. The tester should add initials and a date in the comments column. If the test failed, the tester is required to add additional information about the failure. The status cell will color code based on the test results. The comments cell will color code when a test result exists but no information is entered. Save this test plan with a name formatted as "term-swen-261-sec-letter name", e.g. 2171-swen-261-10-a Speedy Racers.xslx. Submit this file per the instructions specified for the sprint submissions, cross-team testing, and Freshman Seminar testing.
Team Name | 2181-swen-261-11-c
Testing Team Name | 2181-swen-261-13-a

## Test Plan
User Story | Acceptance Criterion | Sprint 1 | Tester initials; date; comments (required if test failed) | Sprint 2 | Tester initials; date; comments (required if test failed) | Sprint 3 | Tester initials; date; comments (required if test failed)
As a Player I want to sign-in so that I can play a game of checkers. | Given that I have not yet signed in when I see the Home page then I must see a means to sign-in. (such as a link or button) |  | J.A.;10/14/2018;LGTM
| Given that I am not signed-in when I do click on the sign-in link then I expect to be taken to the Signin page, with a means to enter a player name. |  | J.A.;10/14/2018;LGTM
| Given that no one else is using my name when I enter my name in the sign-in form and click the Sign-in button then I expect system to reserve my name and navigate back to the Home page. |  | J.A.;10/14/2018;LGTM
| Given that no one else is using my name when I enter a name with a double quote (`"`) then I expect the system to reject this name and return the sign-in form. (Note: double quote is not a valid character in a Player's name.) |  | J.A.;10/14/2018;LGTM
| Given that someone else with my name has signed-in when I enter my name in the sign-in form then I expect the system to reject my sign-in and return the sign-in form. I can then choose a different user name. |  | J.A.;10/14/2018;LGTM
| Given that I have signed in when I see the Home page then I must see a means to sign-out. (such as a link or button) Thus the sign-in and sign-out links need to alternate and never been seen together or not at all. |  | J.A.;10/14/2018;LGTM
| Given that I am signed-in when I click on the sign-out link then I expect the system to sign me out, release my name for use by other users, and then return me to the Home page. |  | J.A.;10/14/2018;LGTM
| Given that I am signed-in when I navigate to the Home page then I expect to see a list of all other signed-in players. (NOTE: in the next story you will use this list to pick opponents for checkers games.) |  | J.A.;10/14/2018;LGTM
| Given that I am not signed-in when I navigate to the Home page then I expect to see a message of how many players are signed-in but not a list of them (for privacy reasons). |  | J.A.;10/14/2018;LGTM
As a Player I want to start a game so that I can play checkers with an opponent. | Given that I'm signed in when I view the Home page then I can start a game by selecting a player listed on the Home page. |  | J.A.;10/14/2018;LGTM
| Given that the player I selected isn't yet in a game when I select that player then the system will begin a checkers game and assign me as the starting (Red) player and my opponent as the White player. |  | J.A.;10/14/2018;LGTM
| Given that the player I selected is already in a game when I select that player then the system will return me to the Home page with an error message. |  | J.A.;10/14/2018;LGTM
| Given that I'm waiting for a game when another player selects a game with me then the system will automatically send me to the Game View from the Home page. NOTE: the `home.ftl` HTML includes a `<meta>` tag that tells the browser to refresh the game every 5 seconds; thus you need to update the `GetHomeRoute` controller to handle the situation when a player is assigned a game. |  | J.A.;10/14/2018;LGTM
| Given a valid, initial game board when I drag a piece to a white space then the piece should not be droppable. |  | J.A.;10/14/2018;LGTM
| Given a valid, initial game board when I drag a piece to an occupied space then the piece should not be droppable. |  | J.A.;10/14/2018;LGTM
| Given a valid, initial game board when I drag a piece to an open space then the piece should be droppable. NOTE: In this Story the drop action should not do anything; piece movement will be the focus of future stories. |  | J.A.;10/14/2018;LGTM
| Given a valid, initial game board when I view the board in the browser then my pieces are oriented on the bottom of the board grid just like I would see the board if I were playing in the physical world. |  | J.A.;10/14/2018;LGTM
As a Player I want to move my pieces forward so that I can prepare to jump my opponent's pieces. | Given its a Player's turn when they load the game then they have the ability to move pieces |  | P.A;11/6/2018;
| Given a Space is a valid move when I check the Space then I want the Piece to move to the valid Space |  | P.A;11/6/2018;
| Given that it is a Player`s turn when I try to move to an invalid space then I stay in the same `space` and can try to make another move |  | P.A;11/6/2018;
As a Player I want to have my piece become a king so that I can move and jump in any direction diagonally. | Given a `Piece` has not been jumped **when** I move the `Piece` to the end of the `Board` **then** I expect the `Piece` to become of type `King` |  | P.A;11/6/2018;
| **Given** a `Piece` has become a `King` **when** the page refreshes **then** I expect to see two `Piece`s stacked on top of one another to designate the piece as a `King` `Piece` |  | P.A;11/6/2018;
| **Given** a `Piece` has just become a `King` **when** the page refreshes **then** I expect the `Player` to not be able to move again (their turn is over) |  | P.A;11/6/2018;
As a Player I want to be able to move backwards so that I can move my piece in any direction diagonally. | Given I have a King when I go to move normally then it should move like a normal Piece |  | P.A;11/6/2018;
| Given I have a King when I go to move backward then the move should be valid if it is a black Space and it is not occupied |  | P.A;11/6/2018;
As a Player I want to submit my successful move so that I can end my turn successfully. | **Given** I have made a move **when** I click submit turn **then** it should become my opponent's turn. |  | P.A;11/6/2018;
| **Given** I haven't made a move **when** I click submit turn **then** it should remain my turn until I make a move and click submit turn. |  | P.A;11/6/2018;
As a Player I want to be able to undo my last valid move before I submit my turn so that I can make sure to make the most optimal move on my turn. | **Given** It is a `Player`s turn **when** they click the reverse move button **then** I expect the system to reverse the last move they made. |  | P.A;11/6/2018;
| **Given** Its a `Players` turn **when** the `Player` hasn't made a move and clicks the reverse move button **then** the system doesn't reverse any moves |  | P.A;11/6/2018;
| **Given** Its not a `Players` turn **when** the`Player` attempts to reverse their move by clicking the button **then** the system shouldn't reverse any moves |  | P.A;11/6/2018;
As a Player, I want to sign-out so that I can leave the system. | **Given** that I signout **when** the page reloads **then** I expect to go to the home page. |  | P.A;11/6/2018;
| **Given** that I am in game **when** I click the signout button **then** I want my opponent to get a win. |  | P.A;11/6/2018;
| **Given** the other `Player` clicks the signout button **when** the game reloads **then** I should be returned to the lobby |  | P.A;11/6/2018;
| **Given** that I clicked the signout button **when** the page reloads **then** I expect my information be removed from the server cause GDPR. |  | P.A;11/6/2018;
| **Given** that I am not currently playing **when** someone tries to signin with my previous username **then** I expect them to be able to. |  | P.A;11/6/2018;
As a player, I want to be able to forfeit any game at any time so that I can blame it on bad internet when I am losing. | **Given** that it is my turn or my opponents turn **when** I click the forfeit button **then** I expect to forfeit the game. |  | P.A;11/6/2018;
| **Given** that I forfeited the game **when** the page reloads **then** I expect to go back to the game menu. |  | P.A;11/6/2018;
| **Given** that I forfeited the game **when** the page reloads **then** I expect to gain a loss. |  | P.A;11/6/2018;
| **Given** that my opponent forfeits the game **when** the page reloads **then** I expect to go back to the game menu.**Given** that my opponent forfeits the game **when** the page reloads **then** I expect to gain a win. |  | P.A;11/6/2018;
As a player, I want to be able to win the game so that I can brag about it to my opponent. | **Given** a `Player` **when** they have captured all of the other `Player`'s `Piece`s **then** the winner receives a win message/page. |  | P.A;11/6/2018;
| **Given** a `Player` **when** the other `Player` forfeits **then** the winner receives a win message/page |  | P.A;11/6/2018;
| **Given** that I have won the game **when** the page reloads **then** I expect to gain a win |  | P.A;11/6/2018;
As a player, I want to be able to lose the game so that the game can be over. | **Given** a `Player` **when** they have all of their `Piece`s captured **then** the `Player` receives a loss message/page |  | P.A;11/6/2018;
| **Given** a `Player` **when** the `Player` forfeits **then** the `Player` receives a loss message/page |  | P.A;11/6/2018;
| **Given** that I have lost the game **when** the page reloads **then** I expect to gain a loss |  | P.A;11/6/2018;